	Objective	Action	Success Criteria	Time Scale/ / Completion	Resources: Staffing, Time, Money, CPD	Monitoring	Evaluation & Further Action
1.	Review current format for annual report to parents	Investigate statutory requirement + consultation with parents about any proposed changes	Any changes, if approved, are fully justified, and communicated to all stakeholders before implementation	Summer term	Time made available for discussions with teaching staff, parents, and students	Leadership Team & Staff Wellbeing Committee	Recommendations shared with Governors TLC Committee.
2.	Reduce time spent by teachers on planning and preparing lessons	Each department to review their scheme of work (SOW) and share and store resources & learning activities	Departments that currently do not routinely share planning and preparation report an improvement	Collaborative work to begin in summer term and continue over next year	Department time, Planning, preparation and assessment time and gained time in the second half of the summer term	Leadership team to include check on SOW and planning and preparation within meeting schedule with Head of Departments (HOD); Staff Wellbeing Committee	Progress shared with Governors’ TLS Committee + staff workload survey January to assess impact
3.	Provide training on staff wellbeing and specifically on how to maintain a reasonable work-life balance or on how to manage a large workload	Provide training to provide advice which helps / leadership team, line managers and individuals to review current practice and make reasonable adjustments to working practices	Greater clarity and more guidance given about what is expected and required regarding work-life balance	Training provided by beginning of new academic year for all staff	Funding for training	Leadership team & Staff Wellbeing Committee	Annual wellbeing report to Governors
4.	Improve equality of opportunity for staff seeking promotion	Develop strategies to encourage underrepresented staff into management & leadership roles by: implementing specific advice for all stakeholders for reference-writing; use of secondments	Staff feedback is positive about the impact of the strategy; evidence that more women are applying for management & leadership posts and are successful	Easter	Continuing professional development (CPD) and time for research	Leadership team & Staff Wellbeing Committee	Progress shared with Governors
5.	Review and amend, where necessary, support staff appraisal policy and procedures so that all support staff receive annual appraisal and have access to appropriate CPD	Create working party to make recommended changes for implementation from September	All support staff have an annual appraisal	Summer term	Training for line managers, where required	Leadership team & Staff Wellbeing Committee	Progress shared with Governors